## Daily report
Date | Location | Work
2023-02-15 | Central Computers | Discuss RMA process, and checks the environment + test devices + technical engineer+ training. Repair 1/2 fail 4U8G-ROME/N
2023-02-16 | NV data Center onsite support | Onsite support to swap two 4U8G-ROME/N with Central Computers in NV datacenter.
2023-02-17 | USA ASI visits USA AIC onsite support | ASI will like to get our AM5 and GENOWA barebone and MBs asap. Also request PO shipping on time. AIC onsite support for EYPCD8-2T BIOS update issue and 4U8G-ROME questions.
2023-02-21 | Central Computers NVIDIA face to face meeting with RMA team | Repaire 1/4 4U8G-ROME/N, but get x16->x8 issue, and now is doing more verify. They ask for pick up RMA system form Central Computers instead of shipping out. Sales George Deng will handle it internally. Some 1U2N2G-B550 BIOS update slowly.-> TSD Richard will onsite check it. 4U8G-ROME/N bandwidth downgrade from x16-> x8 issue-> Now four fail system is in Central Computers, and NVIDIA datacenter all fine. We are narrow down which parts cause this issue, and will bring fail parts back to HQ. 4U8G-ROME/N raid issue-> We get one fail rail, and will take it back for ME team.
2023-02-22 | Central Computers | Troubleshooting the no-post 4U8G system with 2 MBs brought from HQ, both of them having downgraded bandwidth for 2 slots. Golden Sample systems reportedly to have arrived at Central Computers.
2023-02-23 | AirBNB/ Central Computers/ NTT Data Center | Con called with OnLogic, Resolved the 4U8G system bandwidth downgrade issue, On site troubleshooting at NTT data center for NVIDIA's 1U2N2G systems
2023-02-24 | Central Computers | First 4U8G buffer ready, examining on 2nd 4U8G, issue reproduced
2023-02-28 | Central Computers | Testing on 2nd and 3rd 4U8G to make sure the issue could be reproduced as well. Found different issues and uncertain root cause/ solution.
2023-03-01 | Central Computers | Testing the 4th 4U8G, similar symptoms to 3rd one.
2023-03-02 | AirBNB/ Central Computers/ ASA (Racklive) | 1. OnLogic weekly con-call 2. Ask NVIDIA to try “lsusb –v” and “lspci –vvv” on the slow booting 1U2N2G nodes 3. Central Computers to recover 4U8G systems, preparation for shipping 2 systems back to HQ 4. AIC on-site support for 4U8G NIC card issue @Racklive/ASA
2023-03-03 | Central Computers/ DHL station | 1. Sorting and wrapping up systems for shipping back to HQ via DHL 2. DHL miscommunication so we had to take the 2 systems to DHL station by ourselves. DHL Tracking#: 4300352766
2023-03-06 | Central Computers | 1. Check the components shipped from TW 2. Check room 447 at CC 3. Redo 4th 4U8G system testing
2023-03-07 | Central Computers | 1. Moved NV RMA and Golden Sample systems to R447 2. Redo 4th 4U8G system testing 3. Replied NVIDIA's concern to 1U2N2G slow booting issue ASAP and ready to provide BIOS to NV any given time
2023-03-08 | Central Computers/ AMD | 1. Set up workbench and planning for room 447 layout. 2. Unboxed golden sample systems 3. Attended AMD Server SI Summit with Michelle, Meg, George.